## Startup
Test | Procedure | Result | Passed | Failed
Fake Startup | Double click on the file "LBCB Operation Manager Project.lvproj" | LabVIEW should start up and display the project tree
| Double click on "LBCB Operations Manager.vi" and "Mixed Mode Widget.vi" | Both vi's should open with a clean arrow
| Press the blue Real button | The button should turn pink and say Fake
| Press the start arrow on the LBCB Operation Manager and then the Mixed Mode Widget | Both widgets should be running. The Mixed Mode target and input mode window should be grayed out.
| Press Start Autobalancing on the LBCB Operation Manager | The auto balance initialization and Command Displacement Difference window should appear
| Select autobalance on all auto balance windows that appear. | A warning popup should show up. After ok'ing the popup, the system should start autobalancing. After it is balanced there will most likely be numerous limit faults because the fake initial position is deliberately skewed. The limits will need to be adjusted to correct these faults before any further testing is done.
| Press control on one or both LBCBs | The Mixed Mode Widget should now allow inputs
Real Startup | Open up the OM Latest Build folder and double click on the "LBCB Operation Manager" executable | Two widgets should be running. For the Mixed Mode widget, target and input mode window should be grayed out.
| Press Start Autobalancing on the LBCB Operation Manager | The auto balance initialization and Command Displacement Difference window should appear
| Select autobalance on all auto balance windows that appear. | A warning popup should show up. After ok'ing the popup, the system should start autobalancing. After it is balanced there will most likely be numerous limit faults because the fake initial position is deliberately skewed. The limits will need to be adjusted to correct these faults before any further testing is done.
| Press control on one or both LBCBs | The Mixed Mode Widget should now allow inputs
| Check the difference between command and displacement for all of the actuators and DOFs. | The differences should be insignificant. If they are not the LBCB will jump to its initial position once oil pressure is applied
| For the small LBCBs turn low pressure on. | Verify that the forces have not changed significantly
| For the large LBCBs turn low pressure on and unlock the actuators one at a time starting with the Z actuators. | Verify that the forces have not changed significantly
| Switch to high pressure | The forces will jump somewhat but then settle to an equilibrium. This equilibrium is zero unless the LBCB is connected to a specimen. If a specimen is connected then the equilbrium will be close to the last position the LBCB was moved to before it was shut down.

## Displacement Tests
Test | Procedure | Result | Passed | Failed | Notes
Start | Real Startup procedure needs to done up to the point where the control for each LBCB is turned on. Oil pressure should not be used for this test. | The Mixed Mode widget should be ready to accept commands.
Target Patterns | Set Target Pattern to Clear Targets and press Apply | No Targets should be displayed
| Set Target Pattern to Reset to Zero and press Apply | All displacements and rotations for all LBCBs should be displayed in the Targets window with values of zero
| Set Target Pattern to Displacements & Rotations and press Apply | All displacements and rotations for all LBCBs should be displayed in the Targets window with their current value
| Set Target Pattern to Displacements Only and press Apply | All displacements for all LBCBs should be displayed in the Targets window with their current value
| Set Target Pattern to Rotations Only and press Apply | All rotations for all LBCBs should be displayed in the Targets window with their current value
| Set Target Pattern to Forces & Moments and press Apply | All forces and moments for all LBCBs should be displayed in the Targets window with their current value
| Set Target Pattern to Forces Only and press Apply | All forces for all LBCBs should be displayed in the Targets window with their current value
| Set Target Pattern to Moments Only and press Apply | All moments for all LBCBs should be displayed in the Targets window with their current value
Manual input complete step | Input a target of displacement Dx within the displacement limits and press "Set Target" | Start button should blink
Input a ramp time of 10 seconds
| Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be the same as the target. The MM State should be 'Idle' at the end of the ramp.
| Select 'Reset Targets To Zero' target pattern and click on 'Apply' | Target should consist of all 6 displacement DOFs set to zero. 'Start' button should blink.
| Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be all zeros. The MM State should be 'Idle' at the end of the ramp.
Repeat test for Dy
Repeat test for Dz
Repeat test for Rx
Repeat test for Ry
Repeat test for Rz
Repeat test for multiple DOFs and the other LBCB if available
Repeat test for the target patterns "Displacements Only", "Rotations Only", and "Displacements & Rotations"
Manual input with 'Stop' button | Input a target of displacement Dx within the displacement limits and press "Set Target" | Start button should blink
Input a ramp time of 10 seconds
| Press start. | Mixed Mode State display should indicate the start of a ramp.
| Press stop while the MM State is at 'Ramping' | MM State should be 'Idle'. The current position should not be the target
| Press Set Target. Do not change the value of the target | Start button should blink
| Press Start | Ramp should resume from the current position to the original target. Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. The MM State should be 'Idle' at the end of the ramp.
| Select 'Reset Targets To Zero' target pattern and click on 'Apply' | Target should consist of all 6 displacement DOFs set to zero. 'Start' button should blink.
| Press start. | Mixed Mode State display should iterate through 'Ramp'.
| Press stop during the hold state | The Mixed Mode State display should be 'Idle'
Manual Input with a limit fault | Input a target displacement for Dx beyond the Dx limit and press "Set Target". | Start button should blink
| Press start | The ramp should run until the DOF reaches its limit. At this point the MM state display should be 'Idle', The limit fault light should be red, and a message should be displayed that indicates which DOF has faulted.
| Open the limits display and extend the limit so that the fault is cleared. | The fault light should turn green. The fault message should clear. The command for the faulted DOF should not change significantly.
Repeat test for Dy
Repeat test for Dz
Repeat test for Rx
Repeat test for Ry
Repeat test for Rz
Repeat test using the actuator displacement limits for all six actuators
Manual Input Global/Local toggles | Input a target of displacement Dx that is less than half way to the displacement limits and press "Set Target". | Start button should blink
Input a ramp time of 10 seconds
| Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be the same as the target. The MM State should be 'Idle' at the end of the ramp. Record the resulting commands and displacements as 'target 1'
Open the Offsets window and set offsets for both command and measured displacements. Press OK to exit the window
| Click on the 'Global' button to switch it to 'Local' | Command and measured displacements should be extremely close to zero.
| Enter another target that is a small increment past zero and press "Set Target" | Start button should blink
| Press the start button | After the ramp is completed the command and displacement should display the small increment. The other displacements should still be zero. Record these commands and displacments as target 2.
| Switch from Local to Global | The displayed commands and displacements should equal target 2 + target 1.
| Enter a target that is a small increment past the current position and press "Set Target". | Start button should blink
| Press start | After the ramp is completed the command and displacement should display the change in displacement. Record these commands and displacements as target 3.
| Switch from Global to Local | The displayed commands and displacements should equal target 3 - target 1.
| Open the limits display and check the Local limit for a DOF. Record the global limit also. Close the limits display and set a target that is just beyond the local limit and press "Set Target". | Start button should blink
| Press Start | The ramp should run until the DOF reaches its limit.. At this point the MM state display should be 'Idle', The limit fault light should be red, and a message should be displayed that indicates which DOF has faulted.
| Switch from Local to Global | The command should be slightly beyond the global limit.
| Clear the fault by extending the limit. Switch from Global to Local | The fault light should turn green. The fault message should clear. The command for the faulted DOF should not change significantly.
| Select the reset to zero target pattern and press apply. | The start button should blink.
| Press Start | After the ramp runs, all commands and displacements should be zero.
| Swtich from Local to Global | The commands and displacements should equal target 1.
Repeat test for Dy
Repeat test for Dz
Repeat test for Rx
Repeat test for Ry
Repeat test for Rz
Repeat test for multiple DOFs and the other LBCB if available
Input File Run/Pause/Stop/Reset/Fault | Select Input File Mode
| Press Load and select an input file for each LBCB being tested that is within the limits of the DOFs being controlled for the first few steps. Later on in the test there needs to be a target that exceeds a limit. | Pause/Running should be paused.
| Press Run | The accept button should blink. Pause/Running should be running.
| Press Accept | The start button should blink. The accept button stops blinking.
| Press start. | The start button stops blinking. The ramp for the first target should complete. The accept button should blink and the next target should be displayed when the ramp is complete.
| Press Decline | Pause/Running should be paused. The accept button stops blinking.
| Press Run | The accept button should blink. Pause/Running should be running.
| Press Accept | The start button should blink.
| Press stop. | Pause/Running should be paused. The start button should stop blinking
| Switch Propose:Manual to Auto and Press Run | Pause/Running should be running. The start button should start blinking.
| Switch Execute:Manual to Auto and Press Start | Multiple targets are executed until a target exceeds a limit and a fault is generated. The fault light should become red and a message indicating the DOF that has faulted should be displayed. Pause/Running should be paused.
| Open the Limits display and check the Local limit for a DOF. Record the global limit also. Close the limits display and set a target that is just beyond the largest target in the input file. | The fault light should turn green. The fault message should clear. The command for the faulted DOF should not change significantly.
| Press Run | The rest of the targets should be executed. After the input file is done, paused/running should be at paused. Make sure that all of the targets were executed.
| Press Reset and then press Run | The input file should start from the beginning.
| Press Pause | Pause/Running should be paused.
| Press Run | Test execution should continue from the current target.
NTCP | Move the LBCBs to a position close to the nominal origin but not to exactly zero
| Set the offsets and switch from Global to Local coordinates | All of the displacments should read zero
| Switch to NTCP mode and press "Connect NTCP" | The Socket widget should appear and be running
Open up a command window. Change to the "OM Latest Build" folder located at "C:\Documents and Settings\All Users\Desktop\OM Latest Build"
| Type "testNtcpLink.pl --lbcb=?" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press the Accept button | The Start button should blink
| Press the start button | The step should run. After it is completed the next step is sent from the script. The Dx should be at -1. The Accept button should be blinking.
| Press the Decline button | The command window should display "ABORTING PROPOSE COMMAND". The script should send another step with Dx = 1. The Accept button should be blinking
| Press the Accept button and then the Stop button | The command window should display "ABORTING EXECUTE COMMAND". The script should send another step with Dx = -1. The Accept button should be blinking.
| Set the limit for Dx to something more than -1. Press Accept and then Start | The ramp should run until the limit is reached. The command window should display "ABORTING EXECUTE COMMAND". The script should send another step with Dx = 1. The Accept button should be blinking.
| Press "Disconnect NTCP" and type <CTRL> C in the command window | The Socket widget should disappear. The Script should stop running.
| Type "testNtcpLink.pl --lbcb=? --option=1" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after the propose message. At this point NTCP should disconnect and the Socket widget will disappear
| Type "testNtcpLink.pl --lbcb=? --option=2" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after the OM accepts the propose message. At this point NTCP should disconnect and the Socket widget will disappear
| Type "testNtcpLink.pl --lbcb=? --option=3" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after the execute message. At this point NTCP should disconnect and the Socket widget will disappear
| Type "testNtcpLink.pl --lbcb=? --option=4" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after the OM finishes the ramp. At this point NTCP should disconnect and the Socket widget will disappear
| Type "testNtcpLink.pl --lbcb=? --option=5" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after sending a get-control-point message. At this point NTCP should disconnect and the Socket widget will disappear
| Type "testNtcpLink.pl --lbcb=? --option=6" in the command window where ? Is the number of LBCBs you are controlling | The script should start running. The Mixed Mode window will have a blinking Accept button. The Targets window will have a target of 1 for the DX of each LBCB. The test stats window should display step "1 0 4"
| Press Accept and then Start. While the ramp is running switch both Execute and Propose buttons to Auto. | The script will execute three steps. At the fourth step the script will send a close-session command to the OM after the OM returns the control point data. At this point NTCP should disconnect and the Socket widget will disappear

## Configuration Tests
Test | Procedure | Result | Passed | Failed | Notes
OM Setup Test | In the OM Latest Build folder, make a copy of the Config folder so that the configuration can be restored at the end of the test
| Open up the OM Latest Build folder and double click on the "OM Setup" executable | OM Setup should display with the Load button blinking
| Select 1/5 scale two box and press Load | OM Setup will show the saved values for the Actuator Limits.
| Change all of the limit values to unique values | The Save button should be blinking
Switch to LBCB2 and enter unique values for each limit.
| Press Save and then OK | OM Setup should exit
| Restart the OM Setup program and load the 1/5 scale 2 box configuration | Verify that all of the limit values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Cartesian Limits | Verify that all of the limit values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Autobalance | Verify that all of the values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Timing and Logging | Verify that all of the values are the same as what was entered.
| Repeat the value entry tests for LBCB Position | Verify that all of the values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Mixed Mode | Verify that all of the values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Calibration | Verify that all of the values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for Channel Names | Verify that all of the values for both LBCBs are the same as what was entered.
| Repeat the value entry tests for External Sensors | Verify that all of the values for both LBCBs are the same as what was entered.

## Force Control Tests
Test | Procedure | Result | Passed | Failed | Notes
Start | Real Startup procedure needs to done up to the point where the control for each LBCB is turned on. Oil pressure should not be used for this test. | The Mixed Mode widget should be ready to accept commands.