## Displacement Tests
Test | Procedure | Result | Passed | Failed
Manual input complete step | 1. Input a target of displacements within the displacement limits | Start button should blink
2. Input a ramp time of 10 seconds
| 3. Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be the same as the target. The MM State should be 'Idle' at the end of the ramp.
| 4. Select 'Reset Targets To Zero' target pattern and click on 'Apply' | Target should consist of all 6 displacement DOFs set to zero. 'Start' button should blink.
| 5. Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be all zeros. The MM State should be 'Idle' at the end of the ramp.
Manual input with 'Stop' button | 1. Input a target of displacements within the displacement limits | Start button should blink
2. Input a ramp time of 10 seconds
| 3. Press start. | Mixed Mode State display should indicate the start of a ramp.
| 4. Press stop while the MM State is at 'Ramping' | MM State should be 'Idle'. The current position should not be the target
| 5. Type a zero at one of the DOFs and click away. Do not change the value of the target | Start button should blink
| 6. Press Start | Ramp should resume from the current position to the original target. Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. The MM State should be 'Idle' at the end of the ramp.
| 7. Select 'Reset Targets To Zero' target pattern and click on 'Apply' | Target should consist of all 6 displacement DOFs set to zero. 'Start' button should blink.
| 8. Press start. | Mixed Mode State display should iterate through 'Ramp'.
| 9. Press stop during the hold state | The Mixed Mode State display should be 'Idle'
Manual Input with a limit fault | 1. Input a target of displacements where one DOF is set beyond the limit. | Start button should blink
| 2. Press start | The ramp should run until the DOF reaches its limit. At this point the MM state display should be 'Idle', The limit fault light should be red, and a message should be displayed that indicates which DOF has faulted.
| 3. Open the limits display and extend the limit so that the fault is cleared. | The fault light should turn green. The fault message should clear. The command for the faulted DOF should not change significantly.
| 4. Repeat these steps with other DOFs. | Results should be the same.
Manual Input Global/Local toggles | 1. Input a target of displacements that are less than half way to the displacement limits. | Start button should blink
2. Input a ramp time of 10 seconds
| 3. Press start. | Mixed Mode State display should iterate through 'Ramp', 'Stab', and 'Hold'. Command at the end of the ramp should be the same as the target. The MM State should be 'Idle' at the end of the ramp. Record the resulting commands and displacements as 'target 1'
4. Open the Offsets window and set offsets for both command and measured displacements. Press OK to exit the window
| 5. Click on the 'Global' button to switch it to 'Local' | Command and measured displacements should be extremely close to zero.
| 6. Enter another target that is a small increment past zero | Start button should blink
| 7. Press the start button | After the ramp is completed the command and displacement should display the small increment. The other displacements should still be zero. Record these commands and displacments as target 2.
| 8. Switch from Local to Global | The displayed commands and displacements should equal target 2 + target 1.
| 9. Enter a target that is a small increment past the current position. | Start button should blink
| 10. Press start | After the ramp is completed the command and displacement should display the change in displacement. Record these commands and displacements as target 3.
| 11. Switch from Global to Local | The displayed commands and displacements should equal target 3 - target 1.
| 12. Open the limits display and check the Local limit for a DOF. Record the global limit also. Close the limits display and set a target that is just beyond the local limit | Start button should blink
| 13. Press Start | The ramp should run until the DOF reaches its limit.. At this point the MM state display should be 'Idle', The limit fault light should be red, and a message should be displayed that indicates which DOF has faulted.
| 14. Switch from Local to Global | The command should be slightly beyond the global limit.
| 15. Clear the fault by extending the limit. Switch from Global to Local | The fault light should turn green. The fault message should clear. The command for the faulted DOF should not change significantly.
| 16. Select the reset to zero target pattern and press apply. | The start button should blink.
| 17. Press Start | After the ramp runs, all commands and displacements should be zero.
| 18. Swtich from Local to Global | The commands and displacements should equal target 1.
Input File Run/Pause/Stop/Reset/Fault | 1. Select an input file for each LBCB being tested that is within the limits of the DOFs being controlled for the first few steps. Later on in the test there needs to be a target that exceeds a limit. | Pause/Running should be paused.
| 2. Press Load | Pause/Running should be paused.
| 3. Press Run | The accept button should blink. Pause/Running should be running.
| 4. Press Accept | The start button should blink. The accept button stops blinking.
| 5. Press start. | The start button stops blinking. The ramp for the first target should complete. The accept button should blink and the next target should be displayed when the ramp is complete.
| 6. Press Decline | Pause/Running should be paused. The accept button stops blinking.
| 7. Press Run | The accept button should blink. Pause/Running should be running.
| 8. Press Accept | The start button should blink.
| 9. Press stop. | Pause/Running should be paused. The start button should stop blinking
| 10. Switch Propose:Manual to Auto and Press Run | Pause/Running should be running. The start button should start blinking.
11. Switch Execute:Manual to Auto and Press Start